Pre-Install for LSDE basic software installation

| Task | Description | Date Complete | Signoff |
| --- | --- | --- | --- |
| Create /extract directory at the OS level on LIS | Server control scripts and extracted data files |  |  |
| Create LSDE directory on LIS Mumps/Cache | Routines and Globals are installed in this area |  |  |
| Install LSDE external server | Windows server 2003,Windows XP, Windows 7, AIX, Linux, etc |  |  |
| Define LSDE directory on external server | Extracted data will be placed in this directory |  |  |

LSDE Basic Software Installation Worksheet

| Task | Role | Est. Hours | Start Date | Finish Date | Comments | Signoff |
| --- | --- | --- | --- | --- | --- | --- |
| - Set remote access (VPN, remote desktop,etc) | IT |  |  |  |  |  |
| - Install software in LSDE directory | LCS | 2.5 |  |  |  |  |
| - Setup globals | LCS | 1.5 |  |  |  |  |
| - Install LSDE utilities | LCS | 2.0 |  |  |  |  |
| - Configure utilities | LCS | 1.5 |  |  |  |  |
| - Test extract | LCS | 2.0 |  |  |  |  |
| - Install system scripts | LCS | 2.0 |  |  |  |  |
| - Test OS scripts | LCS | 1.0 |  |  |  |  |
| - Staff training and documentation review | LCS/LIS | 4.0 |  |  |  |  |
| - Close project | LIS/LCS | 1.O |  |  |  |  |

Total 17.5 hours

LSDE Full Installation Worksheet

 To be determined

| Task | Role | Est. Hours | Start Date | Finish Date | Comments | Signoff |
| --- | --- | --- | --- | --- | --- | --- |
| - Site specific design and modifications | LCS/LIS |  ~30 |  |  |  |  |
| - Remote login (VPN, Web, desktop) | IT |  ~3.0 |  |  |  |  |
| - LIS system login for LCS staff | IT |  ~2.0 |  |  |  |  |
| - Install servers and other hardware | IT/LCS |  |  |  |  |  |
| - Setup directory where extracted data will be send and test | IT/LCS | 2.0 |  |  |  |  |
| - Create FTP username and password | IT | 1.0 |  |  |  |  |
| - Create LSDE directory | IT/LCS | 1.0 |  |  |  |  |
| - Setup merge/copy of routines from LAB to LSDE directory | IT |  |  |  |  |  |
| - Create system extract directory | IT | 2.0 |  |  |  |  |
| - Install extract routines in LSDE directory | LCS | 2.0 |  |  |  |  |
| - Modify extract routines per site specifications | LCS |  |  |  |  |  |
| - Install menu utilities in LAB directory | LCS | 1.0 |  |  |  |  |
| - Modify menu utilizes per site | LCS | 2.0 |  |  |  |  |
| - Install Globals in LSDE directory | LCS | 1.0 |  |  |  |  |
| - Install system scripts in extract directory | LCS | 1.0 |  |  |  |  |
| - Define server and email addresses | LCS | 1.0 |  |  |  |  |
| - Merge globals from LAB to LSDE | IT/LCS |  ~4-28 |  |  |  |  |
| - Test global merge | IT/LCS | 3.0 |  |  |  |  |
| - Test system server scripts | LCS | 3.0 |  |  |  |  |
| - Modify server scripts as needed | LCS |  |  |  |  |  |
| - Test extract routines | LCS | 16.0 |  |  |  |  |
| - Modify extract routines as needed | LCS |  |  |  |  |  |
| - Prepare LAB and LSDE directories for full extraction test | LCS | 2.0 |  |  |  |  |
| - Start full extraction test | LCS |  |  |  |  |  |
| - Verify extracted data on server | IT/LCS | 2.0 |  |  |  |  |
| - Optimize extraction process | IT/LCS | 1.0 |  |  |  |  |
| - Began LSDE full extraction | LCS | 1.0 |  |  |  |  |
| - Verify extracted data | LCS | 2.0 |  |  |  |  |
| - Test Incremental extraction (3 days) | LCS | 3.0 |  |  |  |  |
| - Verify incremental extract data | LCS | 3.0 |  |  |  |  |
| - Test and verify LSDE utilities (Function LSDE) | LIS/LCS | 4.0 |  |  |  |  |
| - Setup incremental extract in LAB ^LBI(20 startup table | LCS | 1.0 |  |  |  |  |
| - Began daily incremental extract process | LIS/LCS | 1.0 |  |  |  |  |
| - Monitor extraction for 7 days | LIS/LCS | 7.0 |  |  |  |  |
| - Client user training and troubleshooting. | LIS/IT/LCS |  ~ 4.0 |  |  |  |  |
| - Complete install | LIS/IT/LCS |  ~2.0 |  |  |  |  |

Total 100.0 hours